## Sheet1
Iteration #1 | Feature
Date of milestone | Nov 9 2024
Features in scope | Connection Pooling Implementation, Domain adding API, Domain DNS verification, ETCD Service Discovery, Client-side key Decryption, mTLS Security Certificates for inter-service authentication, Inbox creation, Persistent Queue System for Domain verification, Registration and Login, Database setup, Integrity checks, Service side load balancer, Session Managment & Authentication
Features implemented | Connection Pooling Implementation, ETCD Service Discovery, Client-side key Decryption, mTLS Security Certificates for inter-service authentication, Persistent Queue System for Domain verification, Registration and Login, Database setup, Integrity checks, Session Managment & Authentication
Features in deficit this Iteration | Service side load balancer, Domain DNS verification, Inbox creation
Iteration Comments & Summary | I'm happy with the progress so far, I've been picking up Go, gRPC, and ETCD along the way, and I've now (hopefully) solidified the project structure and API layout. All the foundational planning is in place, so Iteration 2 will be focused solely on implementing features. My only concern is the UI, which I’ll begin in Iteration 3, alongside testing. This will hopefully let me prioritize core functionality first, ensuring that I have something to show for my work, and that the backend is feature-complete before diving into the UI and testing phases as things are 100% bound to change in iteration 2.
Iteration #2 | Feature
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #3 | Feature
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #4 | Feature
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #5 | Feature
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #6 | Feature
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary